**Strategic Plan for Live Your Dream Award Winner**

|  |  |  |  |
| --- | --- | --- | --- |
| **Date** | **Activity** | **Need** | **Who** |
| **September** | Contact Organizations   * Churches * Vocational Schools * Colleges * Universities * Shelters * WOA Speaker/Lunch | Copies of Applications  Call organization and identify department or individual  Send out applications  Give club members applications  Brainstorming of ideas for WOA |  |
| **October thru November** | Do workshops at community locations if application assistance is needed | Members to conduct workshop and assist with the application process  Share **LYD** video  Share statistics  Send out Press Release  Invite previous WOA winners  Recruit Judges |  |
| **On or before November 15** | Collect applications  Deadline | Select judges  Deliver applications to judges  Pick up applications |  |
| **December-January** | Read applications  Announce winners | Hold Judging and select a winner using online rubric  Interview individuals  Select winner  Sign media release  Contact all applicants | 3 non-Soroptimist judges |
|  |  | Provide next steps and goals beyond cash award for WOA  Share statistics for need to support individual  Post WOA goals  Review goals/objectives/outcomes  Develop a 3 year action plan |  |
|  | Do presentation at SI meetings/lunch or After Glow | Create a Profile of winner  Publish story in newspaper  Invite winner to WOS lunch |  |
| **3 years** | Provide On-going support | Honor **LYD** winner at recognition luncheon  Support for 3 year action plan   * Mentoring/education * Child support * Financial support * Employment support/resources * Entrepreneurial assistance/CBU seminar * Give winner a seat at the SI lunch table * Quarterly interviews each year for 3 years |  |
| **Feb 1** | **District Level Judging Deadline** |  |  |
| **March 1** | **Regional Level Deadline** |  |  |
| **April 1** | **Federal Level Deadline** |  |  |